🌾 PIXEL-GRAIN

Development Timeline & Sprint Plan

18-Month Agile Roadmap — 4 Phases

Version: v1.0  |  Date: June 2025  |  Author: Divyansh (Krrish)

# 1. Overview

Pixel-Grain follows a 2-week sprint cadence across 4 development phases spanning 18 months. Each sprint has defined deliverables, acceptance criteria, and a definition of done (DoD). The roadmap prioritizes delivering a testable MVP at the end of Phase 1 (Month 3) for pilot deployment with a partner FPO.

# 2. Team Composition

| Role | Count | Phase Joining | Responsibility |
| --- | --- | --- | --- |
| Lead Engineer (Founder) | 1 | Phase 1 | Architecture, ML pipeline, full-stack |
| Backend Engineer | 1 | Phase 2 | Marketplace, agents, API |
| ML Engineer | 1 | Phase 2 | Model training, dataset curation, inference optimization |
| Frontend Engineer | 1 | Phase 3 | React Native mobile app |
| QA Engineer | 1 | Phase 3 | Test automation, regression, API testing |
| DevOps / Infra | 0.5 (part-time) | Phase 1 | Docker, CI/CD, AWS setup |

# 3. Phase 1 — MVP (Months 1–3, Sprints 1–6)

Sprint 1 (Weeks 1–2): Project Setup & Infrastructure

Django 5.x project scaffold with 6 app structure

Docker Compose: Django + PostgreSQL + Redis + Celery + Nginx

CI/CD pipeline (GitHub Actions): lint, test, build, deploy to staging

Environment config: .env.example, settings/base.py, development.py, production.py

django-allauth + SMS OTP (MSG91 sandbox) for farmer auth

Sprint 2 (Weeks 3–4): Authentication & User Profiles

FarmerProfile and BuyerProfile models with migrations

OTP registration and login flow (phone-based for farmers)

JWT token issuance via DRF SimpleJWT

Role-based permission classes (IsFarmer, IsBuyer, IsAdmin)

Basic Django admin configuration for all models

Sprint 3 (Weeks 5–6): Image Upload & S3 Integration

AWS S3 bucket setup (ap-south-1) with django-storages

POST /api/v1/grading/upload/ endpoint with file validation

Celery task skeleton: run_grading_pipeline (stub — returns mock grade)

GradeReport model + immutability enforcement in save()

Unit tests: upload endpoint, S3 mock, task dispatch

Sprint 4 (Weeks 7–8): ML Model Integration

PyTorch CNN model selection (ResNet-18 base) and initial training on wheat/rice dataset

GrainGrader singleton model loader with memory caching

OpenCV preprocessing pipeline: resize, normalize, augment

Real inference replacing stub in Celery task

Model evaluation: accuracy, F1 per grade class on validation set

Sprint 5 (Weeks 9–10): Listings API

CommodityType model + seed fixtures (wheat, rice, moong dal, chana)

Listing model with state machine (DRAFT → ACTIVE → SOLD/EXPIRED)

POST /listings/ and GET /listings/ with DRF FilterSet (commodity, grade, region, price)

POST /listings/{id}/activate/ endpoint

Listing expiry via Celery Beat periodic task

Sprint 6 (Weeks 11–12): Phase 1 QA & Pilot Deploy

End-to-end integration tests: register → upload → grade → list

pytest coverage ≥ 70% on all Phase 1 code

WeasyPrint PDF certificate generation

Staging deployment on AWS EC2 with SSL (Let's Encrypt)

Pilot access for 5 partner farmers (FPO pilot group)

# 4. Phase 2 — Marketplace & Real-time (Months 4–6, Sprints 7–12)

Sprint 7 (Weeks 13–14): Real-time Bidding (WebSockets)

Django Channels + daphne + channel_redis setup

BidConsumer WebSocket consumer with group messaging

Bid model with status machine (PENDING → ACCEPTED/REJECTED)

POST /marketplace/bids/ REST endpoint

ws://…/ws/marketplace/{id}/bids/ WebSocket route

Sprint 8 (Weeks 15–16): Fair Price Engine

APMC mandi data integration (REST or scraping from agmarknet.gov.in)

Price recommendation algorithm: mandi_avg × grade_multiplier

suggested_price_per_kg pre-filled on listing creation

Price trend chart data endpoint: GET /analytics/price-trends/

Sprint 9 (Weeks 17–18): Trade Contracts & Buyer Match Agent

Trade model + contract PDF generation (WeasyPrint template)

POST /marketplace/bids/{id}/accept/ flow → Trade creation

Buyer Match Agent Celery task with BuyerProfile JSONB filter

LLM notification message generation (Claude API sandbox)

Sprint 10 (Weeks 19–20): Razorpay Payment Integration

Razorpay order creation on Trade creation

Webhook receiver with HMAC-SHA256 signature verification

Payment status update → payout to farmer (Razorpay X)

Payment failure flow: Trade → PAYMENT_FAILED; listing re-activation

Sprint 11 (Weeks 21–22): Analytics Dashboard

Farmer dashboard: earnings chart, grade history, buyer interest

Buyer dashboard: supply forecast, price trend charts

Admin dashboard: platform health, fraud flags, ML metrics

CSV / PDF export endpoints

Sprint 12 (Weeks 23–24): Phase 2 QA & Production Launch

Load testing: 500 concurrent WebSocket connections (Locust)

Security audit: OWASP Top 10 review

pytest coverage ≥ 80% overall

Production deployment: multi-container ECS or Docker Swarm

Onboard 50 farmers and 10 buyers for beta launch

# 5. Phase 3 — Intelligence & Scale (Months 7–10, Sprints 13–20)

Phase 3 key deliverables (sprint details condensed):

| Sprints | Deliverable |
| --- | --- |
| Sprint 13–14 | LSTM price forecasting model; Price Forecast Agent Celery Beat task |
| Sprint 15–16 | Multilingual onboarding chatbot (Hindi + 4 regional languages) via Claude API |
| Sprint 17–18 | React Native mobile app consuming DRF API (iOS + Android) |
| Sprint 19 | ML model expansion: vegetables (onion, tomato, potato), spices (turmeric, chili) |
| Sprint 20 | Ed-Tech module: gamified crop quality improvement courses; Phase 3 QA |

# 6. Phase 4 — Enterprise & Community (Months 11–18, Sprints 21–36)

Phase 4 key deliverables (sprint details condensed):

| Sprints | Deliverable |
| --- | --- |
| Sprint 21–24 | Cooperative/FPO bulk listing support; org-level accounts; batch upload API |
| Sprint 25–28 | Government scheme integrations: PM-KISAN data linkage; eNAM API bridge |
| Sprint 29–32 | Open API for third-party agri-fintech; API key management; developer portal |
| Sprint 33–36 | Multi-region deployment: separate DB per state cluster (UP, Punjab, Maharashtra); global admin |

# 7. Definition of Done (DoD)

Feature branch merged to main via PR with ≥1 reviewer approval.

Unit tests written and passing; new code maintains ≥80% test coverage.

API endpoint documented in API doc with request/response example.

No critical Sentry errors on staging for 48 hours.

Product Owner sign-off on acceptance criteria.

Deployed to staging; smoke test passed.

# 8. Risk Register

| Risk | Probability | Impact | Mitigation |
| --- | --- | --- | --- |
| ML model accuracy < 85% on diverse grain types | Medium | High | Augment training data; human audit layer for <70% confidence grades |
| APMC mandi API unavailable/unstable | Medium | Medium | Fallback to last-cached prices; manual price input option |
| LLM API costs exceed budget at scale | Low | Medium | Prompt caching; local LLM (Ollama) fallback for chatbot |
| Razorpay webhook failures causing payment disputes | Low | High | Idempotent webhook handler; retry queue; manual reconciliation dashboard |
| Low farmer adoption (digital literacy barrier) | Medium | High | Field agent onboarding; voice-first chatbot; partnership with FPOs |
| PostgreSQL performance at 100k+ listings | Low | Medium | Composite indexes; pgBouncer; read replica for analytics queries |

# 9. Timeline Summary

| Phase | Duration | Sprints | Key Outcome |
| --- | --- | --- | --- |
| Phase 1 — MVP | Month 1–3 | 1–6 (12 weeks) | Working grading + listing platform; 5-farmer pilot |
| Phase 2 — Marketplace | Month 4–6 | 7–12 (12 weeks) | Live bidding, payments, AI agents; 50-farmer beta |
| Phase 3 — Intelligence | Month 7–10 | 13–20 (16 weeks) | Mobile app, multilingual AI, expanded ML |
| Phase 4 — Enterprise | Month 11–18 | 21–36 (32 weeks) | FPO support, eNAM, multi-state deployment |